## Ark1
| Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 End of project
Team & roles | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | End of project
Design: Dorthea | START
Design layout and web design, 5 days
Digital marketing: Samuel
Digital marketing purposes, 3 days
(in collaberation w/ design and front end)
Front end: Mikal and Amelia
Code foundational pages, 2 days
Product and history information, 3 days
Establish contact features for Lofthus, 2 days
Customer register & log in features, 4 days
Shopping cart and Lofthus shop, 4 days | [16 empty] | END OF PROJECT
Software engineer/back end: Gunnar
Secure servers for customer registrations and payments, 2 days
Establish VISA payments in shop, 3 days
Technical support, 4 days | [16 empty] | END OF PROJECT
EVENTS
Daily standup meetings | 08:15-08:30 | 08:15-08:30 | 08:15-08:30 | 08:15-08:30 | 08:15-08:30 | 10:00-10:15 |  | 08:15-08:30 | 08:15-08:30 | 08:15-08:30 | 08:15-08:30 | 08:15-08:30 | 10:00-10:15 |  | 08:15-08:30 | 08:15-08:30 | SUMMARY 09:00-12:00
Customer meeting |  |  |  |  | PO review 08:30-09:15 | [6 empty] | PO review 08:30-09:15
http://www.wemikling.no/project_methodology/2020-04-10_projectmethodology_ca_Mikal-Larssen_report.pdf